## To Do List
Task list
2017-03-30
| Due Today: | 0
| Overdue: | 4
| Done | Description | Due Date | Priority | Assigned to | comments
1 | 1 | meeting 1 | 2017-02-02 | Medium | Josh
2 | 1 | Project presentation | 2017-02-03 | Medium | Josh
| 1 | meeting 2 | 2017-02-07 | Medium | Josh
|  | create collobrative tools | 2017-02-07 | Low | Josh
| 1 | meeting 3 | 2017-02-21 | Medium | Josh
|  | Marketing requirements | 2017-02-21 | Medium | Naz | naz has not proved any evidenced that this task has even been attempted
| 1 | Software and hardware requirements | 2017-02-23 | High | Josh
| 1 | PiBoy hardware soldering | 2017-02-23 | High | Josh
| 1 | meeting 4 | 2017-02-28 | Medium | Josh
|  | Marketing matterials | 2017-02-28 | Medium | Naz | naz has not proved any evidenced that this task has even been attempted
|  | Marketing adverts | 2017-02-28 | Medium | Naz | naz has not proved any evidenced that this task has even been attempted
| 1 | piBoy hardware hotgluing | 2017-03-09 | High | Josh
| 1 | meeting 5 | 2017-03-16 | Medium | Josh
| 1 | meeting 6 | 2017-03-23 | Medium | Josh
| 1 | Piboy software teensy code | 2017-03-23 | High | Josh
|  | Piboy hardware Cartridge | 2017-04-13 | High | Josh
|  | Piboy hardware teensy programming | 2017-04-13 | High | Josh
|  | Piboy production walkthrough | 2017-04-27 | Medium | Josh
0
Setup >

## Assignment Setup
Assignment Setup
The data in the table below supplies the available choices for the Assigned To field. You can modify the entries or add new entries to customize this workbook to fit your needs.
Assigned To
Josh
Naz
< To Do List
Want to view all of the columns?
Press Ctrl + A to select the worksheet, right-click any column heading, and then click Unhide.